## RTM
Requirements Traceability Matrix — Project Horizon
Meridian Manufacturing & Logistics Pvt. Ltd. ¦ Traces stakeholder need → business requirement → UAT test case
Stakeholder / Need | Business Requirement | BR ID | Requirement Summary | Priority | UAT Test Case | TC ID
Rajiv Malhotra (Ops) — cross-warehouse stock visibility | Real-time consolidated stock view | BR-01 | Single-screen stock view across all sites, refreshed ≥ every 15 min | High | Verify dashboard shows matching totals against manual count at 3 sites | TC-01
Deepak Yadav (Warehouse) — barcode put-away/picking | Barcode scanning for put-away/picking/cycle count | BR-02 | Handheld scanning replaces paper-based floor transactions | High | Scan 20 SKUs through put-away and picking; verify system quantities match physical count | TC-02
Rajiv Malhotra (Ops) — proactive stock-out alerts | Configurable low-stock alerts | BR-03 | Alert triggers when stock crosses defined threshold | High | Set threshold on 3 SKUs, deplete stock in test env, confirm alert fires | TC-03
Deepak Yadav (Warehouse) — peak-week performance | System performance under peak load | BR-04 | Response time <3s at 3x current peak transaction volume | High | Run load test simulating 3x peak dispatch-day transaction volume | TC-04
Priya Nair (Procurement) — formal PR-to-PO workflow | Configurable approval workflow | BR-05 | PRs route through plant/category-specific approval before PO issuance | High | Raise a test PR above/below approval threshold; verify correct routing | TC-05
Priya Nair (Procurement) — three-way match | PO/GRN/invoice three-way matching | BR-06 | System flags exceptions where PO, GRN, invoice don't match | Medium | Submit one matched and one mismatched invoice; verify exception flag on the latter | TC-06
Sunita Rao (Finance) — Tally reconciliation | Tally integration | BR-07 | Daily sync of inventory valuation/cost data with Tally | High | Post a transaction, confirm it reflects in Tally within the defined sync window | TC-07
Sunita Rao (Finance) — landed cost | Landed-cost calculation | BR-08 | Freight/duty/insurance apportioned across received import lines | Medium | Process one import GRN with freight/duty inputs; verify calculated landed cost | TC-08
Sunita Rao (Finance) — audit trail | Immutable adjustment log | BR-09 | Every adjustment logged with user, timestamp, reason code; not editable | High | Make a test adjustment, attempt to edit/delete the log entry, confirm it's blocked | TC-09
Arvind Kapoor (IT) — access control & SSO | Role-based access + SSO | BR-10 | Access configurable by warehouse/plant/transaction type; SSO supported | High | Log in via SSO as 2 different roles; verify each sees only permitted screens/actions | TC-10
Arvind Kapoor (IT) — uptime & failover | DR/failover architecture | BR-11 | ≥99.5% uptime SLA with documented failover | High | Review vendor's DR runbook and request a failover test result/report | TC-11
Deepak Yadav (Warehouse) — handheld device support | Mobile/handheld interface | BR-12 | Compatible with standard Android scanner hardware | High | Run put-away/picking transactions on the actual handheld model used on-site | TC-12
Rajiv Malhotra (Ops) — KPI dashboards | Configurable dashboards with export | BR-13 | Fill rate, dead stock and valuation dashboards, exportable to Excel/PDF | High | Open each dashboard, export to Excel and PDF, reconcile figures to source data | TC-13
Status Tracking (fill in during UAT execution — see UAT Plan document)
TC ID | Test Status (Pass/Fail/Blocked/Not Run) | Tested By | Date Tested | Defect ID (if Fail)
TC-01
TC-02
TC-03
TC-04
TC-05
TC-06
TC-07
TC-08
TC-09
TC-10
TC-11
TC-12
TC-13
Every business requirement in the BRD (BR-01 through BR-13) has at least one traced test case here. RFP requirements that are vendor-qualification or contractual items are covered on the 'Non-UAT Coverage' tab. Yellow cells are for the UAT team to fill in during test execution.

## Non-UAT Coverage
RFP Requirements Verified Outside UAT
Vendor-qualification and contractual requirements, verified during evaluation and due diligence rather than by business-user test cases
RFP ID | Requirement | How it is verified
FR-05 | Cycle counting and physical inventory reconciliation workflows (Desirable) | Vendor demo; scored in vendor scorecard
FR-08 | Vendor performance tracking (Desirable) | Vendor demo; scored in vendor scorecard
NFR-03 | Encryption at rest/in transit; compliance certifications | Security review of vendor documentation and certificates
NFR-04 | Data residency and hosting region | Contract clause and IT/Legal review before signing
NFR-05 | Documented, versioned REST API | Technical review of vendor API documentation
NFR-07 | Cloud or hybrid deployment preferred (Desirable) | Vendor proposal review
NFR-09 | Implementation timeline, methodology, named delivery team | Vendor proposal review
NFR-10 | Two or more contactable customer references | Reference calls during evaluation
NFR-11 | Post-go-live support SLA and training plan | Contract SLA schedule review
NFR-12 | Vendor financial stability (Desirable) | Vendor proposal review