## RACI Matrix
RACI Matrix — Project Horizon
R = Responsible (does the work) · A = Accountable (owns the outcome, one per row) · C = Consulted · I = Informed
Activity / Deliverable | Ops Head | Finance Controller | Warehouse Supervisor | Procurement Manager | IT Manager | Business Analyst | Vendor | Steering Committee
Current-state discovery & stakeholder interviews | C | C | C | C | C | R/A | - | I
Business case & cost-benefit analysis | C | C | - | - | C | R/A | - | I
Business case approval to proceed | I | C | - | - | I | R | - | A
RFP authoring & issuance | C | C | C | C | C | R/A | I | I
Vendor demos & proposal evaluation | C | C | C | C | C | R/A | R | I
Vendor scorecard & shortlist recommendation | C | C | C | C | C | R/A | - | I
Final vendor selection decision | I | I | I | I | I | R | - | A
BRD authoring & sign-off (Business Analyst compiles; each function approves its own section) | C | C | C | C | C | R/A | C | I
UAT test case design | C | C | C | C | C | R/A | C | I
UAT execution | R | R | R | R | R | A | C | I
UAT sign-off / go-live decision | C | C | C | C | C | R | I | A
Training delivery | I | I | R/A | I | I | C | R | I
Change communication & rollout | C | C | C | C | C | R/A | C | I
Post-go-live benefit tracking | C | C | C | C | C | R | I | A
Note: 'R/A' means the Business Analyst is both doing the work and accountable for the outcome for that activity — typical for a BA-led discovery/analysis task. Every decision-point row (approval, selection, sign-off) has exactly one 'A'.

## Risk Register
Risk Register — Project Horizon
Likelihood/Impact scored Low=1, Medium=2, High=3. Score = Likelihood x Impact (max 9).
ID | Category | Risk Description | Likelihood | Impact | Score | Mitigation | Owner | Status
R-01 | Financial | Vendor-quoted pricing in formal RFP responses differs materially from the Business-Analyst estimates used in the Business Case | Medium | High | 6 | Treat the current Business Case as directional; re-run the cost-benefit model with actual vendor quotes before final sign-off | Business Analyst | Open
R-02 | Operational | Data migration from LogiTrack Classic surfaces duplicate or inaccurate SKU records during cutover | High | High | 9 | Run a dedicated data-cleansing pass pre-migration; vendor-assisted validation before go-live | IT Manager | Open
R-03 | Adoption | Warehouse staff revert to paper-based picking instead of using handheld scanners | Medium | High | 6 | Floor-based training on real SKUs, laminated quick-reference guides, active supervisor reinforcement in week one | Warehouse Supervisor | Open
R-04 | Technical | Tally sync produces reconciliation discrepancies during the transition period | Medium | Medium | 4 | Run WMS and Tally in parallel for 2 weeks; Finance spot-checks before full cutover | Finance Controller | Open
R-05 | Vendor | Selected vendor (Warehouse360) fails final due diligence (security review or reference check) | Low | High | 3 | NexusWMS retained as a qualified fallback from the existing shortlist; no re-run of RFP needed | Business Analyst | Open
R-06 | Process | Approval-workflow thresholds are misconfigured, delaying PO issuance at go-live | Medium | Medium | 4 | UAT test case TC-05 explicitly validates routing logic before go-live sign-off | Procurement Manager | Open
R-07 | Governance | A key stakeholder is unavailable during vendor evaluation, so a selection decision gets made without full functional input | Low | Medium | 2 | RACI matrix names a backup approver per function to avoid a single-person bottleneck | Business Analyst | Open
R-08 | Scope | Mid-project requests to extend the platform into ERP or transportation-management territory | Medium | Medium | 4 | BRD scope section explicitly excludes ERP/TMS for this phase; any such request goes through a formal change log, not ad hoc | Business Analyst | Open
Highest-scoring risk (R-02, data migration) is also the one with the most direct mitigation already in motion — a dedicated cleansing pass — since it's the risk most likely to derail the go-live date if left unmanaged.